## Read Me
Mobile Charging Repair Simulation - Asset Production Register
Source: 'Mobile charging repair Simulation' storyboard (16pp, modules BC.1 / BC.2 / BC.3). Prepared 21 Aug 2026.
THE DECISION RULE
BLENDER - if the learner must IDENTIFY, LOCATE, ORIENT or MANIPULATE the thing with their hands.
Spatial understanding transfers to a real bench. 65 rows (48 models/effects + 17 animation clips), 87.5 days.
INFOGRAPHIC - if the content is INVISIBLE signal flow, electrical logic, a numeric spec, a named
sequence, or a comparison. 3D adds cost and teaches nothing extra here. 28 graphics, 21 days.
PHOTO/VIDEO - real-world defects and already-sourced footage. 7 items, nearly all already supplied.
RUNTIME/CODE - interaction, state and scoring. Not an art deliverable at all. 7 items, 13.5 days.
THE THREE THINGS THAT MATTER MOST IN THIS BREAKDOWN
1. This course is ONE phone teardown, reused 18 times. B02 (mainboard) appears in 7 of 18 scenes;
B05 (USB-C port) in 5; B28 (hot air station) in 6. Build the master assets to a high standard once.
Mean reuse across the 65 Blender rows is 2.75 scenes each; B32 (bench + lighting) hits 9.
2. Every 'circuit diagram overlay' in the storyboard is an INFOGRAPHIC, not a model. VBUS/GND/CC1/CC2
traces and the Charger IC's internal stages (OVP > buck > current sense) have no visible geometry.
Modelling them would burn weeks and teach less than a clean 2D diagram. See I04 and I09.
3. Infographic does NOT mean stock photo. Every step strip and tool card should use a BLENDER RENDER
as its image (I13, I14, I17-I22). Same assets, second output channel, near-zero extra cost.
WHAT THE STORYBOARD ASKS FOR THAT NEEDS A DECISION BEFORE THE BUILD STARTS
MOLTEN SOLDER (B45) - 'lift away once solder liquifies' is the core skill beat in 5 fixes. A real
Blender fluid sim will NOT export to real-time. Bake to vertex animation + animated shader, or
pre-render that beat as video. Decide before Fix 2 starts. 3 days either way.
HANDS - the storyboard says 'technician using hot-air rework'. Modelling and rigging hands adds
15-20 days and constant clipping problems. Recommend a tool-only convention: the instrument moves,
no hands. Cleaner to read at macro scale and it is what teardown videos already do.
FPC PEEL (B10 / A09) - the ribbon must deform, not cut away. Bone chain or shape keys, baked.
Blender cloth sim does not survive glTF export. A09 cannot start until B10's rig signs off.
MULTIMETER READOUT (U02) - the number must react to probe position, so it is a runtime canvas
texture. Blender supplies the bezel only. Do not bake any digits into the model.
TWO GRAPHICS MISSING FROM THE STORYBOARD THAT YOU SHOULD ADD
I24 Fault symptom > probable cause decision tree. Three symptoms map to six fixes and that map is
never drawn. 0.75 days, and it is the cheapest thing on this list that raises pass rates.
I28 Fix-selection escalation ladder. 'Start with the easiest thing first' is stated in the VO of
BC.1 scene 1 and then never shown as a picture. 0.5 days.
WEB DELIVERY BUDGET (assume low-end Android, 3G)
Per-scene GLB: 8 MB hard ceiling, 5 MB target. Whole course asset set: 25 MB.
Draco mesh compression + KTX2/Basis textures on everything. 2K only for hero parts (B02, B05, B11, B15).
512 shared atlas for bench tools and consumables - they are never the subject of a macro shot.
LOD0 full detail for macro/inspection, LOD1 at 40% for bench-wide shots, LOD2 at 15% for icons.
Tri figures in the register are LOD0 before Draco.
HOW TO READ THE ESTIMATES
Days = one mid-level Blender artist, model + UV + texture + web optimisation, or one designer for
infographics. Excludes VO, translation, QA and runtime engineering other than the U-series rows.
Complexity High rows are the ones to staff with your strongest artist and start first.
HEADLINE NUMBERS
107 distinct assets across 18 scenes. 122.7 person-days total.
Blender 87.5 d (71%) - 48 models/effects + 17 animation clips, 48 clips in all.
Infographic 21 d (17%) - 28 graphics. Runtime/code 13.5 d (11%). Photo/video 0.7 d (supplied).
At 3 Blender artists + 1 designer, that is roughly 6 calendar weeks of art, running in parallel.
9 rows are High complexity and carry 26 days between them - staff those first: B02, B05, B10, B11, B45, A09, A12, U02, U04.

## Asset Register
Asset Register - every visual asset the storyboard calls for
One row per distinct asset. Colour = production route. Filter column D to split the work.
Asset ID | Asset name | Module | Route | Scenes used in | Reuse (scenes) | Why this route | Tri budget (LOD0) | Textures | Anim clips | Est. days | Complexity | Notes / risks
B01 | Phone body shell + removable back cover | BC.1 | BLENDER | BC.1-S1, BC.3-S1, BC.3-S7 | 3 | Learner must orient the handset in their hands and know which way it opens | 18k | 2x1K PBR | 0 | 3 | Med | Model one generic mid-range Android form factor. Back cover as separate mesh so it can be lifted.
B02 | Mainboard (PBA) - populated | BC.1 | BLENDER | BC.1-S1, BC.1-S4, BC.3-S2, BC.3-S3, BC.3-S4, BC.3-S5, BC.3-S6 | 7 | The stage every board-level fix happens on; spatial location of each part is the lesson | 45k | 2K colour + 1K rough/normal | 0 | 4 | High | MASTER ASSET - highest reuse in the whole course. Build once, texture properly, never rebuild.
B03 | Sub-PBA / small daughterboard | BC.1 | BLENDER | BC.1-S3, BC.3-S3 | 2 | Storyboard NOTE says the ribbon may bond to a Sub-PBA instead - needs its own mesh | 8k | 1K shared atlas | 0 | 1 | Low
B04 | Screw set + labelled screw tray | BC.2 | BLENDER | BC.3-S7 | 1 | 'Every screw in its labelled tray slot' is a physical placement habit - must be manipulable | 4k | 512 shared | 0 | 1 | Low | Tray slot labels as a texture, not geometry.
B05 | USB-C female port assembly (shell, insert, 24 pins, mounting legs, gasket) | BC.1 | BLENDER | BC.1-S1, BC.1-S2, BC.2-S3, BC.3-S1, BC.3-S2 | 5 | HERO. Exploded view + 180 deg cutaway + per-pin highlight all need real geometry | 30k | 2K + gold/steel PBR | 2 | 4 | High | Build as 5 named sub-objects so explode + pin highlight are driven by transforms, not separate models.
B06 | USB-C male plug (cable end) | BC.1 | BLENDER | BC.1-S1, BC.2-S3, BC.3-S1, BC.3-S7 | 4 | Insertion + orientation demo | 6k | 1K shared | 0 | 1 | Low
B07 | USB-C cable (curve-deformable) | BC.1 | BLENDER | BC.1-S1, BC.2-S3, BC.3-S7 | 3 | Wiggle test and cable-fault checks need it to bend | 3k | 512 tileable | 1 | 1 | Low | Curve modifier, baked to skinned mesh for glTF export.
B08 | Wall charger adapter (TA) | BC.1 | BLENDER | BC.1-S1, BC.3-S7 | 2 | Start of the charging path; also the 'known-good TA' in every test step | 5k | 1K | 0 | 1 | Low
B09 | Wall outlet / socket plate | BC.1 | BLENDER | BC.1-S1 | 1 | Anchors the path diagram in something familiar | 1k | 512 shared | 0 | 0.5 | Low
B10 | FPC flex ribbon (rigged for bend + peel) | BC.1 | BLENDER | BC.1-S1, BC.1-S3, BC.3-S2, BC.3-S3 | 4 | HERO. The peel-off in Fix 3 is the single most misdiagnosed fault - must deform, not cut | 6k | 1K gold/polyimide | 2 | 3 | High | Bone chain or shape keys. Cloth sim will NOT export to real-time - bake it.
B11 | Board-side ZIF socket + hinged flap + gold pins | BC.1 | BLENDER | BC.1-S3, BC.3-S3 | 2 | HERO. 'Is the flap fully closed?' is the diagnosis - the flap must actually hinge | 14k | 2K gold/black nylon | 2 | 4 | High | Flap on its own pivot. Latched/unlatched are two states the quiz can test.
B12 | Stiffener backing + anchoring solder pads | BC.1 | BLENDER | BC.1-S3, BC.3-S3 | 2 | Named failure point (cracked/dry pads) | 2k | shares B11 atlas | 0 | 0.5 | Low
B13 | Charger IC package + BGA solder ball array | BC.1 | BLENDER | BC.1-S4, BC.3-S4, BC.3-S5 | 3 | Fix 4 is entirely about the balls UNDER the chip - needs a cutaway-capable mesh | 5k | 1K | 1 | 2 | Med | Model the ball array. Cold-joint vs reflowed is a geometry+material variant, see B40.
B14 | Neighbouring SMT component kit (caps, resistors, shields) | BC.1 | BLENDER | BC.1-S4, BC.3-S2, BC.3-S4, BC.3-S5, BC.3-S6 | 5 | 'Without disturbing nearby components' only means something if they are there | 6k | 512 atlas | 0 | 1.5 | Low | Library of ~10 parts, instanced across the board. Cheap, big realism win.
B15 | Battery connector SOCKET (AXF361500, board side) | BC.1 | BLENDER | BC.1-S5, BC.2-S4, BC.3-S6 | 3 | Storyboard asks for a macro product shot AND it is the Fix 6 subject | 10k | 2K gold plating | 1 | 2 | Med | Gold-plating texture detail is what sells this shot. Worth a proper anisotropic material.
B16 | Battery connector HEADER (AXF461500, battery side) | BC.1 | BLENDER | BC.1-S5, BC.2-S4, BC.3-S6 | 3 | The mating half - two-part connector is the teaching point | 8k | shares B15 atlas | 1 | 2 | Med
B17 | Li-po battery pouch + tabs + BMS flex | BC.1 | BLENDER | BC.1-S1, BC.1-S6, BC.2-S4, BC.3-S7 | 4 | Disconnect-first safety rule acts on this object | 7k | 2K aluminium laminate | 1 | 2 | Med
B18 | Digital multimeter + probe leads | BC.2 | BLENDER | BC.2-S1, BC.2-S3, BC.3-S6, BC.3-S7 | 4 | Learner performs the voltage test - probe placement is a motor skill | 9k | 1K + dynamic LCD | 2 | 2 | Med | LCD is a separate material slot driven at runtime (see U02), NOT a baked number.
B19 | USB power meter dongle | BC.2 | BLENDER | BC.2-S1, BC.3-S7 | 2 | Reads the actual current - the 'is it charging slowly' test | 4k | 1K + dynamic display | 0 | 1 | Low
B20 | Magnifying lamp | BC.2 | BLENDER | BC.2-S1, BC.3-S1 | 2 | Named in Fix 1 step 2 | 4k | 1K shared bench atlas | 0 | 1 | Low
B21 | Digital (Dino) microscope | BC.2 | BLENDER | BC.2-S1, BC.3-S1, BC.3-S2 | 3 | 'Inspect under magnification' recurs in 5 of 6 fixes | 6k | 1K shared bench atlas | 0 | 1.5 | Med
B22 | Precision screwdriver set | BC.2 | BLENDER | BC.2-S1, BC.3-S7 | 2 | Opening the phone | 3k | 512 shared | 0 | 1 | Low
B23 | Plastic pry tools / spudger set | BC.2 | BLENDER | BC.2-S1, BC.3-S7 | 2 | Opening the phone without damage | 2k | 512 shared | 0 | 0.5 | Low
B24 | Anti-static wrist band | BC.2 | BLENDER | BC.2-S1 | 1 | ESD discipline - visible on the bench | 2k | 512 shared | 0 | 0.5 | Low
B25 | Anti-static mat | BC.2 | BLENDER | BC.2-S1, BC.3-S1, BC.3-S7 | 3 | Bench surface for every repair scene | 0.5k | 1K tileable | 0 | 0.25 | Low
B26 | PBA holder / board fixture (articulated) | BC.2 | BLENDER | BC.2-S1, BC.3-S2, BC.3-S3, BC.3-S4, BC.3-S5, BC.3-S6 | 6 | 'Hands free instead of holding the board' - the board sits in this in every rework scene | 8k | 1K | 1 | 2 | Med | Jaws need to open/close if you want the 'clamp the board' beat.
B27 | Soldering iron + stand | BC.2 | BLENDER | BC.2-S1, BC.3-S2, BC.3-S3, BC.3-S6 | 4 | Precision joint work; 'always returned to its stand' is a safety beat | 6k | 1K + emissive tip | 1 | 1.5 | Med
B28 | Hot air rework station + nozzle | BC.2 | BLENDER | BC.2-S1, BC.3-S2, BC.3-S3, BC.3-S4, BC.3-S5, BC.3-S6 | 6 | The primary instrument in 5 of the 6 fixes | 10k | 1K + digital display | 1 | 2 | Med | Nozzle must be a separate child object - it is what the learner aims.
B29 | ESD-safe precision tweezers | BC.2 | BLENDER | BC.2-S1, BC.3-S3, BC.3-S5, BC.3-S6 | 4 | Places the new part - a manipulator, not scenery | 2k | 512 shared | 1 | 0.75 | Low
B30 | Fume extractor arm | BC.2 | BLENDER | BC.2-S1 | 1 | 'Running before you ever pick up the iron' - safety framing | 7k | 1K | 0 | 1.5 | Med
B31 | Spare parts tray | BC.2 | BLENDER | BC.2-S1, BC.3-S2, BC.3-S3, BC.3-S6 | 4 | Where the replacement part comes from | 2k | 512 shared | 0 | 0.5 | Low
B32 | Workbench surface + studio lighting rig | BC.2 | BLENDER | BC.2-S1, BC.2-S2, BC.3-S1, BC.3-S2, BC.3-S3, BC.3-S4, BC.3-S5, BC.3-S6, BC.3-S7 | 9 | Shared set. Build the lighting once so every scene matches | 2k | 2K tileable + HDRI | 0 | 1.5 | Med | One lighting rig for the whole course = visual consistency for free.
B33 | Liquid flux bottle + fine brush cap | BC.2 | BLENDER | BC.2-S2, BC.3-S4, BC.3-S5 | 3 | 'Used TWICE in almost every rework job' - learner reaches for it constantly | 2k | 1K label | 0 | 0.75 | Low | Lathe/revolve geometry. The label texture does all the work.
B34 | Desoldering wick spool | BC.2 | BLENDER | BC.2-S2, BC.3-S2, BC.3-S3, BC.3-S6 | 4 | Pad cleaning step in 3 fixes | 2k | 512 + braid normal | 0 | 0.5 | Low
B35 | Solder wire reel | BC.2 | BLENDER | BC.2-S2, BC.3-S2, BC.3-S3, BC.3-S6 | 4 | Forms every new joint | 2k | 512 | 0 | 0.5 | Low
B36 | IPA bottle + lint-free swabs | BC.2 | BLENDER | BC.2-S2, BC.3-S1, BC.3-S3, BC.3-S4 | 4 | Pad cleaning in 4 places | 2k | 1K label | 0 | 0.75 | Low
B37 | UV-curable solder mask bottle + UV lamp | BC.2 | BLENDER | BC.2-S2 | 1 | 'Green oil' - distinctive, learners must recognise it | 4k | 1K label + emissive | 1 | 1 | Low
B38 | Kapton tape roll + pre-cut shielding strips | BC.2 | BLENDER | BC.2-S2, BC.3-S4, BC.3-S5, BC.3-S6 | 4 | 'Heat-resistant tape shielding neighbouring parts' - a placement action in 3 fixes | 1k | 512 | 0 | 0.5 | Low | Loose strips as separate placeable planes.
B39 | SUS-tip cleaning stick + alcohol swab | BC.2 | BLENDER | BC.2-S2, BC.3-S1 | 2 | THE tool for Fix 1, 'never a random sharp object' | 1k | 512 | 1 | 0.5 | Low
B40 | Solder joint state set: good / cold / cracked / bridged / dry | BC.3 | BLENDER | BC.3-S2, BC.3-S3, BC.3-S4, BC.3-S5, BC.3-S6 | 5 | The entire diagnostic curriculum is joint quality. Without these there is nothing to assess | 3k each | 1K solder atlas | 0 | 1.5 | Med | HIGHEST TEACHING VALUE PER DAY IN THE WHOLE LIST. 5 swappable meshes + materials.
B41 | Damaged port variants: bent pins / cracked housing / broken shield tabs | BC.3 | BLENDER | BC.3-S1, BC.3-S2 | 2 | Fix 1 vs Fix 2 branches on 'dust or physical damage?' - learner must see both | 30k | reuses B05 atlas | 0 | 1.5 | Med | Shape keys off B05, not new models.
B42 | Damaged IFC variants: worn pads / torn ribbon / unlatched flap | BC.3 | BLENDER | BC.3-S3 | 1 | Fix 3 trigger condition. Also the 'charges only at one angle' symptom | 6k | reuses B10/B11 | 0 | 1.5 | Med
B43 | Corroded battery connector variant | BC.3 | BLENDER | BC.3-S6 | 1 | 'If either half corrodes, the phone behaves like the battery failed' | 10k | reuses B15 | 0 | 0.75 | Low
B44 | Dust / lint / corrosion debris in port (particle set) | BC.3 | BLENDER | BC.3-S1 | 1 | Before/after of Fix 1 needs something to remove | 1k | 512 alpha | 1 | 0.5 | Low | Fake with instanced specks + alpha - do NOT run a particle sim.
B45 | Molten solder: melt, wet-out, wick-up (baked) | BC.3 | BLENDER | BC.3-S2, BC.3-S3, BC.3-S4, BC.3-S5, BC.3-S6 | 5 | 'Lift away once solder liquifies - never pry it cold' is the core skill beat | - | 1K emissive + flipbook | 5 | 3 | High | RISK: real fluid sim does not export to real-time. Bake to vertex animation + animated shader, or pre-render this beat as video.
B46 | Hot air stream + heat shimmer (flipbook) | BC.3 | BLENDER | BC.3-S2, BC.3-S3, BC.3-S4, BC.3-S5, BC.3-S6 | 5 | Makes the invisible tool visible; also communicates 'safe distance, 5mm away' | - | 512 flipbook | 2 | 2 | Med | Bake to a sprite sheet in Blender, play in the runtime.
B47 | Flux wet-surface shader | BC.3 | BLENDER | BC.3-S4, BC.3-S5 | 2 | 'Apply flux around the edges' needs a visible result | - | shader only | 1 | 1 | Low
B48 | Solder smoke wisp (flipbook) | BC.3 | BLENDER | BC.3-S2, BC.3-S3, BC.3-S6 | 3 | Reinforces why the fume extractor runs | - | 512 flipbook | 1 | 1 | Low
A01 | ANIM: USB-C port exploded view (shell / housing / flex tail) | BC.1 | BLENDER | BC.1-S2 | 1 | Storyboard: 'Final shot: exploded view' | - | - | 1 | 1 | Low
A02 | ANIM: port 180 deg cutaway rotation + sequential pin highlight | BC.1 | BLENDER | BC.1-S2 | 1 | Storyboard: 'rotating 180 deg to show the pin row', 'each pin lights up sequentially' | - | - | 1 | 1.5 | Med | Pin highlight driven by runtime material swap, camera move baked in Blender.
A03 | ANIM: FPC path reveal, port to mainboard | BC.1 | BLENDER | BC.1-S3 | 1 | Storyboard: 'animated view of the flex cable running from port to mainboard' | - | - | 1 | 1 | Low
A04 | ANIM: ZIF flap open / close + pin contact | BC.1 | BLENDER | BC.1-S3, BC.3-S3 | 2 | Storyboard: 'latch/flap lifting open... flap closing to lock' | - | - | 1 | 0.75 | Low
A05 | ANIM: macro zoom onto Charger IC | BC.1 | BLENDER | BC.1-S4 | 1 | Storyboard: 'animated zoom into a small chip package' | - | - | 1 | 0.5 | Low
A06 | ANIM: battery connector mate / unmate | BC.1 | BLENDER | BC.1-S5, BC.2-S4, BC.3-S6 | 3 | Storyboard: 'third panel can show the two halves mated together' | - | - | 2 | 1 | Low
A07 | ANIM: Fix 2 - port desolder + lift | BC.3 | BLENDER | BC.3-S2 | 1 | Steps 3-4. 'Never pry it off cold' shown, not told | - | - | 1 | 1.5 | Med
A08 | ANIM: Fix 2 - align new port, shield tabs then signal pins | BC.3 | BLENDER | BC.3-S2 | 1 | Steps 6-7. The ORDER is the lesson | - | - | 1 | 1.5 | Med
A09 | ANIM: Fix 3 - IFC ribbon peel-off | BC.3 | BLENDER | BC.3-S3 | 1 | Steps 3-4. 'Do not force it, do not pull on the port end' | - | - | 1 | 1.5 | High | Depends on B10 rig. Schedule after B10 signs off.
A10 | ANIM: Fix 3 - place ribbon, solder ONE corner pad first | BC.3 | BLENDER | BC.3-S3 | 1 | Steps 7-8. Sequence-critical | - | - | 1 | 1.5 | Med
A11 | ANIM: Fix 4 - IC reflow without lifting | BC.3 | BLENDER | BC.3-S4 | 1 | 'The chip itself is never lifted off the board' - contrast with Fix 5 | - | - | 1 | 1 | Med
A12 | ANIM: Fix 5 - IC desolder, place, reflow | BC.3 | BLENDER | BC.3-S5 | 1 | The deepest board-level fix | - | - | 1 | 1.5 | High
A13 | ANIM: Fix 6 - battery connector replace | BC.3 | BLENDER | BC.3-S6 | 1 | Steps 3-5, with tape shielding the battery flex | - | - | 1 | 1.25 | Med
A14 | ANIM: Fix 1 - cleaning stick shake, upper + lower slots | BC.3 | BLENDER | BC.3-S1 | 1 | 'About 10 times per side' - a rhythm, needs motion | - | - | 1 | 0.75 | Low
A15 | ANIM: multimeter probe placement (port + cable end-to-end) | BC.2 | BLENDER | BC.2-S3, BC.3-S6 | 2 | Two distinct probe placements, both must be precise | - | - | 2 | 1 | Med
A16 | ANIM: phone reassembly + screw-to-slot sequence | BC.3 | BLENDER | BC.3-S7 | 1 | 'Every screw in its labelled tray slot' | - | - | 1 | 1.5 | Med
A17 | ANIM: battery disconnect (the golden rule) | BC.2 | BLENDER | BC.2-S4, BC.3-S2, BC.3-S3, BC.3-S5, BC.3-S6 | 5 | 'Disconnect the battery FIRST' opens 5 of 6 fixes - one clip, reused | - | - | 1 | 0.5 | Low | Build once, replay at the head of every fix.
I01 | Charging path system diagram (Wall > Cable > Port > IC > Battery) | BC.1 | INFOGRAPHIC | BC.1-S1 | 1 | A causal chain, not an object. 3D adds nothing; a clean 2D chain is the mental model | - | 2048x1152 PNG | 0 | 0.5 | Low | This single graphic is the spine of the whole course - reference it back in every module.
I02 | The three common problems card (no charge / slow / intermittent) | BC.1 | INFOGRAPHIC | BC.1-S1, BC.3-S1 | 2 | A taxonomy - text and icons | - | 1600x900 | 0 | 0.25 | Low
I03 | USB-C pin function table (Row A / Row B contacts) | BC.1 | INFOGRAPHIC | BC.1-S2 | 1 | It is literally a table. Modelling 24 labelled pins in 3D to read a table wastes days | - | 2048x1152 | 0 | 0.5 | Low
I04 | USB-C signal trace overlay (VBUS / GND / CC1-CC2 / D+- / SBU) | BC.1 | INFOGRAPHIC | BC.1-S2 | 1 | Electrical signal paths are INVISIBLE inside the part. No 3D geometry exists to model | - | 2048x1152 + transparent layer | 0 | 0.75 | Low | Author as a transparent overlay so it can sit on top of the live 3D port.
I05 | USB-C reversibility explainer (flip the plug, one row lines up) | BC.1 | INFOGRAPHIC | BC.1-S2 | 1 | 'Rows A and B are electrical mirrors' is a logical relationship, best as a 2-state diagram | - | 2048x1152 | 0 | 0.5 | Low
I06 | Port component callout labels (9 named parts) | BC.1 | INFOGRAPHIC | BC.1-S2 | 1 | Leader lines + names, drawn over the 3D render | - | transparent overlay set | 0 | 0.5 | Low | Overlay on B05, not a standalone picture.
I07 | IFC layered cross-section (latch / pins / FPC / stiffener / pads) | BC.1 | INFOGRAPHIC | BC.1-S3 | 1 | A stack-up you cannot see even with the part in hand | - | 2048x1152 | 0 | 0.75 | Low
I08 | IFC circuit chain (Port > flex tail > IFC socket > PBA traces) | BC.1 | INFOGRAPHIC | BC.1-S3 | 1 | Storyboard asks for it explicitly as a circuit diagram overlay | - | transparent overlay | 0 | 0.5 | Low
I09 | Charger IC internal block diagram (OVP > buck > current sense > output, + I2C + thermal) | BC.1 | INFOGRAPHIC | BC.1-S4 | 1 | MUST be 2D. These are functional stages inside silicon - there is no visible geometry to model | - | 2048x1152 | 0 | 1 | Med | Do NOT let anyone model this in 3D. The reference image already shows the right treatment.
I10 | Charger IC pin / stage callouts | BC.1 | INFOGRAPHIC | BC.1-S4 | 1 | Labels over the 3D chip | - | transparent overlay | 0 | 0.5 | Low
I11 | Battery connector spec card (2.40mm / 1.80mm, part numbers) | BC.1 | INFOGRAPHIC | BC.1-S5 | 1 | Dimension arrows and part numbers are annotation over a render, not geometry | - | 2048x1152 | 0 | 0.5 | Low
I12 | Battery + BMS protection callouts (PTC, SCP IC, BSI/TH, OVP, UVP) | BC.1 | INFOGRAPHIC | BC.1-S6 | 1 | Protection ICs on the BMS strip are too small to read in 3D and are identified by name, not shape | - | 2048x1152 | 0 | 0.75 | Low
I13 | Tool hero cards x14 (feature callouts per tool) | BC.2 | INFOGRAPHIC | BC.2-S1 | 1 | Spec bullets and 'what it does' text. Card layout, with the Blender render as the hero image | - | 14 x 1600x1200 | 0 | 3.5 | Med | USE BLENDER RENDERS AS THE CARD IMAGE - do not buy stock photos. Consistency is the point.
I14 | Consumable product cards x8 | BC.2 | INFOGRAPHIC | BC.2-S2 | 1 | Same pattern - purpose, when to use, cautions | - | 8 x 1600x1200 | 0 | 2 | Med | Same rule: Blender renders inside the card.
I15 | Multimeter anatomy card (dial, jacks, display, leads) | BC.2 | INFOGRAPHIC | BC.2-S1, BC.2-S3 | 2 | Named part identification on a flat panel - a labelled diagram beats a rotatable model | - | 2048x1152 | 0 | 0.5 | Low
I16 | Multimeter test procedure, 2 panels (port voltage / cable continuity) | BC.2 | INFOGRAPHIC | BC.2-S3 | 1 | Expected READINGS (~5V, 0.0 + beep) are numbers and pass/fail rules | - | 2048x1152 | 0 | 0.5 | Low
I17 | Fix 1 step strip (6 panels) | BC.3 | INFOGRAPHIC | BC.3-S1 | 1 | A numbered procedure the learner will re-scan later. Strips beat video for recall | - | 2400x1600 | 0 | 0.75 | Low | Build each panel from a Blender render of the matching animation frame.
I18 | Fix 2 step strip (8 panels) | BC.3 | INFOGRAPHIC | BC.3-S2 | 1 | 9 ordered steps, order-critical | - | 2400x1600 | 0 | 1 | Med | Frames pulled from A07/A08.
I19 | Fix 3 step strip (6 panels) | BC.3 | INFOGRAPHIC | BC.3-S3 | 1 | 10 ordered steps | - | 2400x1600 | 0 | 0.75 | Low | Frames pulled from A09/A10.
I20 | Fix 4 step strip (reflow) | BC.3 | INFOGRAPHIC | BC.3-S4 | 1 | 6 steps + the 'let it cool undisturbed' caution | - | 2400x1600 | 0 | 0.75 | Low
I21 | Fix 5 step strip (PMIC replace) | BC.3 | INFOGRAPHIC | BC.3-S5 | 1 | 8 steps, Level-4 repair - needs a written record | - | 2400x1600 | 0 | 0.75 | Low
I22 | Fix 6 step strip (battery connector) | BC.3 | INFOGRAPHIC | BC.3-S6 | 1 | 7 steps | - | 2400x1600 | 0 | 0.75 | Low
I23 | Testing & closing-up flowchart | BC.3 | INFOGRAPHIC | BC.3-S7 | 1 | A decision flow with a loop-back ('if the fault returns, do not close the job') | - | 2048x1400 | 0 | 0.5 | Low
I24 | Fault symptom > probable cause decision tree | BC.3 | INFOGRAPHIC | BC.3-S1, BC.3-S7 | 2 | NOT IN THE STORYBOARD BUT MISSING. Three symptoms map to six fixes - learners need the map | - | 2400x1600 | 0 | 0.75 | Med | RECOMMENDED ADDITION. Cheapest single thing you can add to raise pass rates.
I25 | Golden safety rule card (disconnect the battery FIRST) | BC.2 | INFOGRAPHIC | BC.2-S4, BC.3-S2, BC.3-S3, BC.3-S5, BC.3-S6 | 5 | One rule, repeated at the head of 5 fixes. Must be instantly recognisable | - | 1600x900 | 0 | 0.25 | Low
I26 | Temperature & spec reference card (380-450C, 350-450C iron, 5mm standoff) | BC.2 | INFOGRAPHIC | BC.2-S1, BC.3-S2, BC.3-S3 | 3 | Numbers. Never model a number | - | 1600x900 | 0 | 0.25 | Low
I27 | THE SHAPE RULE card: rigid metal box vs flat gold ribbon | BC.3 | INFOGRAPHIC | BC.3-S2, BC.3-S3 | 2 | Storyboard shouts 'REMEMBER THE SHAPE RULE'. Fix 2 vs Fix 3 is the commonest confusion in the course | - | 2048x1152 | 0 | 0.5 | Med | Pair it with a side-by-side Blender render of B05 and B10. Highest-leverage graphic in BC.3.
I28 | Fix-selection escalation ladder (Fix 1 > Fix 6, cheapest first) | BC.3 | INFOGRAPHIC | BC.3-S1, BC.3-S7 | 2 | 'Check each part one by one, starting with the easiest' is the whole method | - | 2048x1400 | 0 | 0.5 | Low | RECOMMENDED ADDITION - implied throughout, never drawn.
P01 | Real macro photo: damaged battery connector, bent pins | BC.3 | PHOTO/VIDEO | BC.3-S6 | 1 | Real corrosion and bent-pin damage is hard to model convincingly and you already have the shot (p16) | - | supplied | 0 | 0.1 | Low | Pair a real photo beside the 3D as a 'this is what it looks like on a real bench' panel.
P02 | Real photo: realme mainboard, connector locations circled | BC.1 | PHOTO/VIDEO | BC.1-S5 | 1 | Supplied in the storyboard; grounds the 3D in a real handset | - | supplied | 0 | 0.1 | Low
P03 | Real photo: Li-po battery exterior + BMS strip | BC.1 | PHOTO/VIDEO | BC.1-S6 | 1 | Supplied; the label text is part of the lesson | - | supplied | 0 | 0.1 | Low
V01 | Video (linked): battery connector explainer | BC.1 | PHOTO/VIDEO | BC.1-S5 | 1 | Already sourced - youtube.com/watch?v=pyIzVRzNs4M | - | external | 0 | 0.1 | Low | Clear rights before embedding. Prefer re-shooting or linking out.
V02 | Video (linked): multimeter usage | BC.2 | PHOTO/VIDEO | BC.2-S3 | 1 | Already sourced - youtube.com/watch?v=H8edOCVbsbs | - | external | 0 | 0.1 | Low
V03 | Video (linked): USB-C port replacement short | BC.3 | PHOTO/VIDEO | BC.3-S2 | 1 | Already sourced - youtube.com/shorts/xnwgaWB929M | - | external | 0 | 0.1 | Low
V04 | Video (linked): PMIC replacement short | BC.3 | PHOTO/VIDEO | BC.3-S5 | 1 | Already sourced - youtube.com/shorts/T32jucv8Kcg | - | external | 0 | 0.1 | Low
U01 | Quick Check MCQ engine + feedback | BC.1 | RUNTIME/CODE | BC.1-S7 | 1 | Interaction logic, not an asset | - | - | 0 | 1.5 | Med
U02 | Dynamic multimeter / power-meter readout (runtime texture) | BC.2 | RUNTIME/CODE | BC.2-S3, BC.3-S6, BC.3-S7 | 3 | The number must respond to WHERE the learner puts the probe. Cannot be baked in Blender | - | canvas texture | 0 | 2 | High | Blender supplies the bezel; the runtime draws the digits.
U03 | Tool-selection / drag-and-drop interaction | BC.2 | RUNTIME/CODE | BC.2-S1, BC.2-S2, BC.3-S1 | 3 | 'Pick the right tool' assessment | - | - | 0 | 2 | Med
U04 | Step gating, ordered-sequence validation + checklist state | BC.3 | RUNTIME/CODE | BC.3-S1, BC.3-S2, BC.3-S3, BC.3-S4, BC.3-S5, BC.3-S6, BC.3-S7 | 7 | Order-critical steps (shield tabs BEFORE signal pins) are only teachable if wrong order fails | - | - | 0 | 3 | High | THE core mechanic of BC.3. Budget properly.
U05 | Magnification / microscope camera mode | BC.3 | RUNTIME/CODE | BC.3-S1, BC.3-S2, BC.3-S3, BC.3-S4, BC.3-S5 | 5 | 'Inspect under magnification' recurs constantly - a camera state, not a model | - | - | 0 | 1 | Med
U06 | Language switcher + VO playback sync | BC.1 | RUNTIME/CODE | BC.1-S1, BC.2-S1, BC.3-S1 | 3 | VO script column exists for every scene; multilingual is a ConveGenius baseline | - | - | 0 | 2 | Med | VO timing must drive the Blender clip playhead, not run alongside it.
U07 | Progress, scoring and telemetry | BC.1 | RUNTIME/CODE | BC.1-S7, BC.3-S7 | 2 | Needed to prove competency for a TVET credential | - | - | 0 | 2 | Med
| TOTAL (all routes) | [7 empty] | 48 | 122.7 |  | Person-days. See Effort Summary for the split by route and module.

## Blender Build List
Blender build list - 3D assets, animation clips and baked effects
Sequenced. Build the master assets in Wave 1; every later scene reuses them.
Wave | Asset ID | Asset name | Tri budget | Textures | Anim clips | Est. days | Complexity | Build notes
WAVE 1 - master assets (everything else depends on these)
| B02 | Mainboard (PBA) - populated | 45k | 2K colour + 1K rough/normal | 0 | 4 | High | MASTER ASSET - highest reuse in the whole course. Build once, texture properly, never rebuild.
| B01 | Phone body shell + removable back cover | 18k | 2x1K PBR | 0 | 3 | Med | Model one generic mid-range Android form factor. Back cover as separate mesh so it can be lifted.
| B05 | USB-C female port assembly (shell, insert, 24 pins, mounting legs, gasket) | 30k | 2K + gold/steel PBR | 2 | 4 | High | Build as 5 named sub-objects so explode + pin highlight are driven by transforms, not separate models.
| B10 | FPC flex ribbon (rigged for bend + peel) | 6k | 1K gold/polyimide | 2 | 3 | High | Bone chain or shape keys. Cloth sim will NOT export to real-time - bake it.
| B11 | Board-side ZIF socket + hinged flap + gold pins | 14k | 2K gold/black nylon | 2 | 4 | High | Flap on its own pivot. Latched/unlatched are two states the quiz can test.
| B32 | Workbench surface + studio lighting rig | 2k | 2K tileable + HDRI | 0 | 1.5 | Med | One lighting rig for the whole course = visual consistency for free.
|  | Wave subtotal |  |  |  | 19.5
WAVE 2 - remaining charging-path hardware
| B03 | Sub-PBA / small daughterboard | 8k | 1K shared atlas | 0 | 1 | Low | Storyboard NOTE says the ribbon may bond to a Sub-PBA instead - needs its own mesh
| B04 | Screw set + labelled screw tray | 4k | 512 shared | 0 | 1 | Low | Tray slot labels as a texture, not geometry.
| B06 | USB-C male plug (cable end) | 6k | 1K shared | 0 | 1 | Low | Insertion + orientation demo
| B07 | USB-C cable (curve-deformable) | 3k | 512 tileable | 1 | 1 | Low | Curve modifier, baked to skinned mesh for glTF export.
| B08 | Wall charger adapter (TA) | 5k | 1K | 0 | 1 | Low | Start of the charging path; also the 'known-good TA' in every test step
| B09 | Wall outlet / socket plate | 1k | 512 shared | 0 | 0.5 | Low | Anchors the path diagram in something familiar
| B12 | Stiffener backing + anchoring solder pads | 2k | shares B11 atlas | 0 | 0.5 | Low | Named failure point (cracked/dry pads)
| B13 | Charger IC package + BGA solder ball array | 5k | 1K | 1 | 2 | Med | Model the ball array. Cold-joint vs reflowed is a geometry+material variant, see B40.
| B14 | Neighbouring SMT component kit (caps, resistors, shields) | 6k | 512 atlas | 0 | 1.5 | Low | Library of ~10 parts, instanced across the board. Cheap, big realism win.
| B15 | Battery connector SOCKET (AXF361500, board side) | 10k | 2K gold plating | 1 | 2 | Med | Gold-plating texture detail is what sells this shot. Worth a proper anisotropic material.
| B16 | Battery connector HEADER (AXF461500, battery side) | 8k | shares B15 atlas | 1 | 2 | Med | The mating half - two-part connector is the teaching point
| B17 | Li-po battery pouch + tabs + BMS flex | 7k | 2K aluminium laminate | 1 | 2 | Med | Disconnect-first safety rule acts on this object
|  | Wave subtotal |  |  |  | 15.5
WAVE 3 - bench tools and consumables (parallelisable, low risk)
| B18 | Digital multimeter + probe leads | 9k | 1K + dynamic LCD | 2 | 2 | Med | LCD is a separate material slot driven at runtime (see U02), NOT a baked number.
| B19 | USB power meter dongle | 4k | 1K + dynamic display | 0 | 1 | Low | Reads the actual current - the 'is it charging slowly' test
| B20 | Magnifying lamp | 4k | 1K shared bench atlas | 0 | 1 | Low | Named in Fix 1 step 2
| B21 | Digital (Dino) microscope | 6k | 1K shared bench atlas | 0 | 1.5 | Med | 'Inspect under magnification' recurs in 5 of 6 fixes
| B22 | Precision screwdriver set | 3k | 512 shared | 0 | 1 | Low | Opening the phone
| B23 | Plastic pry tools / spudger set | 2k | 512 shared | 0 | 0.5 | Low | Opening the phone without damage
| B24 | Anti-static wrist band | 2k | 512 shared | 0 | 0.5 | Low | ESD discipline - visible on the bench
| B25 | Anti-static mat | 0.5k | 1K tileable | 0 | 0.25 | Low | Bench surface for every repair scene
| B26 | PBA holder / board fixture (articulated) | 8k | 1K | 1 | 2 | Med | Jaws need to open/close if you want the 'clamp the board' beat.
| B27 | Soldering iron + stand | 6k | 1K + emissive tip | 1 | 1.5 | Med | Precision joint work; 'always returned to its stand' is a safety beat
| B28 | Hot air rework station + nozzle | 10k | 1K + digital display | 1 | 2 | Med | Nozzle must be a separate child object - it is what the learner aims.
| B29 | ESD-safe precision tweezers | 2k | 512 shared | 1 | 0.75 | Low | Places the new part - a manipulator, not scenery
| B30 | Fume extractor arm | 7k | 1K | 0 | 1.5 | Med | 'Running before you ever pick up the iron' - safety framing
| B31 | Spare parts tray | 2k | 512 shared | 0 | 0.5 | Low | Where the replacement part comes from
| B33 | Liquid flux bottle + fine brush cap | 2k | 1K label | 0 | 0.75 | Low | Lathe/revolve geometry. The label texture does all the work.
| B34 | Desoldering wick spool | 2k | 512 + braid normal | 0 | 0.5 | Low | Pad cleaning step in 3 fixes
| B35 | Solder wire reel | 2k | 512 | 0 | 0.5 | Low | Forms every new joint
| B36 | IPA bottle + lint-free swabs | 2k | 1K label | 0 | 0.75 | Low | Pad cleaning in 4 places
| B37 | UV-curable solder mask bottle + UV lamp | 4k | 1K label + emissive | 1 | 1 | Low | 'Green oil' - distinctive, learners must recognise it
| B38 | Kapton tape roll + pre-cut shielding strips | 1k | 512 | 0 | 0.5 | Low | Loose strips as separate placeable planes.
| B39 | SUS-tip cleaning stick + alcohol swab | 1k | 512 | 1 | 0.5 | Low | THE tool for Fix 1, 'never a random sharp object'
|  | Wave subtotal |  |  |  | 20.5
WAVE 4 - fault-state variants and baked effects
| B40 | Solder joint state set: good / cold / cracked / bridged / dry | 3k each | 1K solder atlas | 0 | 1.5 | Med | HIGHEST TEACHING VALUE PER DAY IN THE WHOLE LIST. 5 swappable meshes + materials.
| B41 | Damaged port variants: bent pins / cracked housing / broken shield tabs | 30k | reuses B05 atlas | 0 | 1.5 | Med | Shape keys off B05, not new models.
| B42 | Damaged IFC variants: worn pads / torn ribbon / unlatched flap | 6k | reuses B10/B11 | 0 | 1.5 | Med | Fix 3 trigger condition. Also the 'charges only at one angle' symptom
| B43 | Corroded battery connector variant | 10k | reuses B15 | 0 | 0.75 | Low | 'If either half corrodes, the phone behaves like the battery failed'
| B44 | Dust / lint / corrosion debris in port (particle set) | 1k | 512 alpha | 1 | 0.5 | Low | Fake with instanced specks + alpha - do NOT run a particle sim.
| B45 | Molten solder: melt, wet-out, wick-up (baked) | - | 1K emissive + flipbook | 5 | 3 | High | RISK: real fluid sim does not export to real-time. Bake to vertex animation + animated shader, or pre-render this beat as video.
| B46 | Hot air stream + heat shimmer (flipbook) | - | 512 flipbook | 2 | 2 | Med | Bake to a sprite sheet in Blender, play in the runtime.
| B47 | Flux wet-surface shader | - | shader only | 1 | 1 | Low | 'Apply flux around the edges' needs a visible result
| B48 | Solder smoke wisp (flipbook) | - | 512 flipbook | 1 | 1 | Low | Reinforces why the fume extractor runs
|  | Wave subtotal |  |  |  | 12.75
WAVE 5 - animation clips (needs the rigs signed off first)
| A01 | ANIM: USB-C port exploded view (shell / housing / flex tail) | - | - | 1 | 1 | Low | Storyboard: 'Final shot: exploded view'
| A02 | ANIM: port 180 deg cutaway rotation + sequential pin highlight | - | - | 1 | 1.5 | Med | Pin highlight driven by runtime material swap, camera move baked in Blender.
| A03 | ANIM: FPC path reveal, port to mainboard | - | - | 1 | 1 | Low | Storyboard: 'animated view of the flex cable running from port to mainboard'
| A04 | ANIM: ZIF flap open / close + pin contact | - | - | 1 | 0.75 | Low | Storyboard: 'latch/flap lifting open... flap closing to lock'
| A05 | ANIM: macro zoom onto Charger IC | - | - | 1 | 0.5 | Low | Storyboard: 'animated zoom into a small chip package'
| A06 | ANIM: battery connector mate / unmate | - | - | 2 | 1 | Low | Storyboard: 'third panel can show the two halves mated together'
| A07 | ANIM: Fix 2 - port desolder + lift | - | - | 1 | 1.5 | Med | Steps 3-4. 'Never pry it off cold' shown, not told
| A08 | ANIM: Fix 2 - align new port, shield tabs then signal pins | - | - | 1 | 1.5 | Med | Steps 6-7. The ORDER is the lesson
| A09 | ANIM: Fix 3 - IFC ribbon peel-off | - | - | 1 | 1.5 | High | Depends on B10 rig. Schedule after B10 signs off.
| A10 | ANIM: Fix 3 - place ribbon, solder ONE corner pad first | - | - | 1 | 1.5 | Med | Steps 7-8. Sequence-critical
| A11 | ANIM: Fix 4 - IC reflow without lifting | - | - | 1 | 1 | Med | 'The chip itself is never lifted off the board' - contrast with Fix 5
| A12 | ANIM: Fix 5 - IC desolder, place, reflow | - | - | 1 | 1.5 | High | The deepest board-level fix
| A13 | ANIM: Fix 6 - battery connector replace | - | - | 1 | 1.25 | Med | Steps 3-5, with tape shielding the battery flex
| A14 | ANIM: Fix 1 - cleaning stick shake, upper + lower slots | - | - | 1 | 0.75 | Low | 'About 10 times per side' - a rhythm, needs motion
| A15 | ANIM: multimeter probe placement (port + cable end-to-end) | - | - | 2 | 1 | Med | Two distinct probe placements, both must be precise
| A16 | ANIM: phone reassembly + screw-to-slot sequence | - | - | 1 | 1.5 | Med | 'Every screw in its labelled tray slot'
| A17 | ANIM: battery disconnect (the golden rule) | - | - | 1 | 0.5 | Low | Build once, replay at the head of every fix.
|  | Wave subtotal |  |  |  | 19.25
|  | BLENDER TOTAL |  |  |  | 87.5 |  | Person-days for one mid-level artist. Waves 2 and 3 parallelise across 3 artists to roughly 7 calendar weeks.

## Infographic List
Infographic list - what should NOT be modelled in 3D
Every item here is invisible signal flow, electrical logic, a number, a sequence or a comparison.
Asset ID | Graphic name | Module | Scenes used in | Why 2D beats 3D here | Output spec | Est. days | Source image
I01 | Charging path system diagram (Wall > Cable > Port > IC > Battery) | BC.1 | BC.1-S1 | A causal chain, not an object. 3D adds nothing; a clean 2D chain is the mental model | 0 | 0.5 | Vector / illustration, no 3D source needed
I02 | The three common problems card (no charge / slow / intermittent) | BC.1 | BC.1-S1, BC.3-S1 | A taxonomy - text and icons | 0 | 0.25 | Vector / illustration, no 3D source needed
I03 | USB-C pin function table (Row A / Row B contacts) | BC.1 | BC.1-S2 | It is literally a table. Modelling 24 labelled pins in 3D to read a table wastes days | 0 | 0.5 | Vector, from USB-C spec
I04 | USB-C signal trace overlay (VBUS / GND / CC1-CC2 / D+- / SBU) | BC.1 | BC.1-S2 | Electrical signal paths are INVISIBLE inside the part. No 3D geometry exists to model | 0 | 0.75 | Vector overlay, sits on live B05
I05 | USB-C reversibility explainer (flip the plug, one row lines up) | BC.1 | BC.1-S2 | 'Rows A and B are electrical mirrors' is a logical relationship, best as a 2-state diagram | 0 | 0.5 | Vector / illustration, no 3D source needed
I06 | Port component callout labels (9 named parts) | BC.1 | BC.1-S2 | Leader lines + names, drawn over the 3D render | 0 | 0.5 | Overlay on B05 render
I07 | IFC layered cross-section (latch / pins / FPC / stiffener / pads) | BC.1 | BC.1-S3 | A stack-up you cannot see even with the part in hand | 0 | 0.75 | Vector / illustration, no 3D source needed
I08 | IFC circuit chain (Port > flex tail > IFC socket > PBA traces) | BC.1 | BC.1-S3 | Storyboard asks for it explicitly as a circuit diagram overlay | 0 | 0.5 | Vector / illustration, no 3D source needed
I09 | Charger IC internal block diagram (OVP > buck > current sense > output, + I2C + thermal) | BC.1 | BC.1-S4 | MUST be 2D. These are functional stages inside silicon - there is no visible geometry to model | 0 | 1 | Vector / illustration, no 3D source needed
I10 | Charger IC pin / stage callouts | BC.1 | BC.1-S4 | Labels over the 3D chip | 0 | 0.5 | Overlay on B13 render
I11 | Battery connector spec card (2.40mm / 1.80mm, part numbers) | BC.1 | BC.1-S5 | Dimension arrows and part numbers are annotation over a render, not geometry | 0 | 0.5 | Overlay on B15 + B16 render
I12 | Battery + BMS protection callouts (PTC, SCP IC, BSI/TH, OVP, UVP) | BC.1 | BC.1-S6 | Protection ICs on the BMS strip are too small to read in 3D and are identified by name, not shape | 0 | 0.75 | Traced from supplied photo P03
I13 | Tool hero cards x14 (feature callouts per tool) | BC.2 | BC.2-S1 | Spec bullets and 'what it does' text. Card layout, with the Blender render as the hero image | 0 | 3.5 | Blender renders of B18-B32 (do not buy stock)
I14 | Consumable product cards x8 | BC.2 | BC.2-S2 | Same pattern - purpose, when to use, cautions | 0 | 2 | Blender renders of B33-B39
I15 | Multimeter anatomy card (dial, jacks, display, leads) | BC.2 | BC.2-S1, BC.2-S3 | Named part identification on a flat panel - a labelled diagram beats a rotatable model | 0 | 0.5 | Vector / illustration, no 3D source needed
I16 | Multimeter test procedure, 2 panels (port voltage / cable continuity) | BC.2 | BC.2-S3 | Expected READINGS (~5V, 0.0 + beep) are numbers and pass/fail rules | 0 | 0.5 | Vector / illustration, no 3D source needed
I17 | Fix 1 step strip (6 panels) | BC.3 | BC.3-S1 | A numbered procedure the learner will re-scan later. Strips beat video for recall | 0 | 0.75 | Frames from A14
I18 | Fix 2 step strip (8 panels) | BC.3 | BC.3-S2 | 9 ordered steps, order-critical | 0 | 1 | Frames from A07 + A08
I19 | Fix 3 step strip (6 panels) | BC.3 | BC.3-S3 | 10 ordered steps | 0 | 0.75 | Frames from A09 + A10
I20 | Fix 4 step strip (reflow) | BC.3 | BC.3-S4 | 6 steps + the 'let it cool undisturbed' caution | 0 | 0.75 | Frames from A11
I21 | Fix 5 step strip (PMIC replace) | BC.3 | BC.3-S5 | 8 steps, Level-4 repair - needs a written record | 0 | 0.75 | Frames from A12
I22 | Fix 6 step strip (battery connector) | BC.3 | BC.3-S6 | 7 steps | 0 | 0.75 | Frames from A13
I23 | Testing & closing-up flowchart | BC.3 | BC.3-S7 | A decision flow with a loop-back ('if the fault returns, do not close the job') | 0 | 0.5 | Vector / illustration, no 3D source needed
I24 | Fault symptom > probable cause decision tree | BC.3 | BC.3-S1, BC.3-S7 | NOT IN THE STORYBOARD BUT MISSING. Three symptoms map to six fixes - learners need the map | 0 | 0.75 | Vector / illustration, no 3D source needed
I25 | Golden safety rule card (disconnect the battery FIRST) | BC.2 | BC.2-S4, BC.3-S2, BC.3-S3, BC.3-S5, BC.3-S6 | One rule, repeated at the head of 5 fixes. Must be instantly recognisable | 0 | 0.25 | Vector / illustration, no 3D source needed
I26 | Temperature & spec reference card (380-450C, 350-450C iron, 5mm standoff) | BC.2 | BC.2-S1, BC.3-S2, BC.3-S3 | Numbers. Never model a number | 0 | 0.25 | Vector / illustration, no 3D source needed
I27 | THE SHAPE RULE card: rigid metal box vs flat gold ribbon | BC.3 | BC.3-S2, BC.3-S3 | Storyboard shouts 'REMEMBER THE SHAPE RULE'. Fix 2 vs Fix 3 is the commonest confusion in the course | 0 | 0.5 | Side-by-side render of B05 vs B10
I28 | Fix-selection escalation ladder (Fix 1 > Fix 6, cheapest first) | BC.3 | BC.3-S1, BC.3-S7 | 'Check each part one by one, starting with the easiest' is the whole method | 0 | 0.5 | Vector / illustration, no 3D source needed
| INFOGRAPHIC TOTAL |  |  |  |  | 21
Amber rows (I24, I28) are NOT in the storyboard - they are recommended additions. 1.25 days combined.
Rule: every step strip and tool card uses a Blender render as its image. Same assets, second output channel.

## Scene Map
Scene map - what each of the 18 scenes needs
Shows the reuse. Very little is built for a single scene.
Scene | Scene name | What the storyboard asks for | Blender assets | Infographics | Photo/Video | Runtime
BC.1-S1 | How a Phone Charges | Wall charger > cable > port > IC > battery, the whole path in 3D on a bench | B01, B02, B05, B06, B07, B08, B09, B10, B17 | I01, I02 |  | U06
BC.1-S2 | The Charging Port | Cutaway, 180 deg rotate, sequential pin highlight, exploded view | B05, A01, A02 | I03, I04, I05, I06
BC.1-S3 | The IFC Connector | Flex ribbon route, ZIF flap open/close, contact pins | B03, B10, B11, B12, A03, A04 | I07, I08
BC.1-S4 | The Charger IC | Macro zoom onto the chip + internal stage block diagram | B02, B13, B14, A05 | I09, I10
BC.1-S5 | The Battery Connector | Photoreal macro of socket + header, then mated | B15, B16, A06 | I11 | P02, V01
BC.1-S6 | The Battery | Pouch, tabs, BMS protection callouts | B17 | I12 | P03
BC.1-S7 | Quick Check | MCQ - no visual asset |  |  |  | U01, U07
BC.2-S1 | Tools on the Workbench | Top-down labelled bench, 14 tools | B18, B19, B20, B21, B22, B23, B24, B25, B26, B27, B28, B29, B30, B31, B32 | I13, I15, I26 |  | U03, U06
BC.2-S2 | Liquids & Consumables | 8 bottles, spools and sticks | B32, B33, B34, B35, B36, B37, B38, B39 | I14 |  | U03
BC.2-S3 | How to Use the Multimeter | Probe placement at the port, then cable continuity | B05, B06, B07, B18, A15 | I15, I16 | V02 | U02
BC.2-S4 | Golden Safety Rule & Recap | Disconnect the battery first | B15, B16, B17, A06, A17 | I25
BC.3-S1 | Fix 1 - Clean the charging port | SUS stick in the slots, before/after dust | B01, B05, B06, B20, B21, B25, B32, B36, B39, B41, B44, A14 | I02, I17, I24, I28 |  | U03, U04, U05, U06
BC.3-S2 | Fix 2 - Replace the port (metal box) | Hot air desolder, pad clean, new port, tabs then pins | B02, B05, B10, B14, B21, B26, B27, B28, B31, B32, B34, B35, B40, B41, B45, B46, B48, A07, A08, A17 | I18, I25, I26, I27 | V03 | U04, U05
BC.3-S3 | Fix 3 - Replace the IFC ribbon | Peel the flex, clean pads, one corner first | B02, B03, B10, B11, B12, B26, B27, B28, B29, B31, B32, B34, B35, B36, B40, B42, B45, B46, B48, A04, A09, A10, A17 | I19, I25, I26, I27 |  | U04, U05
BC.3-S4 | Fix 4 - Reflow the Charger IC | Reheat the BGA balls without lifting the chip | B02, B13, B14, B26, B28, B32, B33, B36, B38, B40, B45, B46, B47, A11 | I20 |  | U04, U05
BC.3-S5 | Fix 5 - Replace the Charger IC | Desolder, place, reflow under magnification | B02, B13, B14, B26, B28, B29, B32, B33, B38, B40, B45, B46, B47, A12, A17 | I21, I25 | V04 | U04, U05
BC.3-S6 | Fix 6 - Replace the battery connector | Hot air, tape shield, new connector | B02, B14, B15, B16, B18, B26, B27, B28, B29, B31, B32, B34, B35, B38, B40, B43, B45, B46, B48, A06, A13, A15, A17 | I22, I25 | P01 | U02, U04
BC.3-S7 | Testing & Closing Up | Reassemble, screws to tray slots, TA + USB test | B01, B04, B06, B07, B08, B17, B18, B19, B22, B23, B25, B32, A16 | I23, I24, I28 |  | U02, U04, U07

## Effort Summary
Effort summary
All figures are formulas over the Asset Register. Change a day estimate there and this updates.
BY PRODUCTION ROUTE |  |  |  |  | READING THIS SHEET
Route | Assets | Anim clips | Est. days | % of days
BLENDER | 65 | 48 | 87.5 | 71.31% | The Blender share of effort is large but it buys the whole course, not one module - the
INFOGRAPHIC | 28 | 0 | 21 | 17.11% | master assets (B02 mainboard, B05 port, B10 flex, B11 ZIF socket) carry 18 scenes between them.
PHOTO/VIDEO | 7 | 0 | 0.7 | 0.5705%
RUNTIME/CODE | 7 | 0 | 13.5 | 11% | Infographics are a small fraction of the days and cover the content 3D genuinely cannot
TOTAL | 107 | 48 | 122.7 | 100% | reach: signal flow, chip-internal stages, spec numbers, ordered procedures, comparisons.
Runtime/code is not an art cost and is under-scoped here on purpose - U04 (ordered-step
BY MODULE |  |  |  |  | validation) is the real core mechanic of BC.3 and deserves its own engineering estimate.
Module | Assets | Anim clips | Est. days | % of days
BC.1 | 40 | 18 | 51.05 | 41.61% | The High-complexity rows are where schedule risk lives: B02, B05, B10, B11, B45, A09, A12, U02, U04.
BC.2 | 34 | 11 | 35.6 | 29.01% | Start those first and give them your strongest people.
BC.3 | 33 | 19 | 36.05 | 29.38%
TOTAL | 107 | 48 | 122.7 | 100%
BY COMPLEXITY
Complexity | Assets | Anim clips | Est. days | % of days
Low | 63 | 15 | 39.2 | 31.95%
Med | 35 | 20 | 57.5 | 46.86%
High | 9 | 13 | 26 | 21.19%
TOTAL | 107 | 48 | 122.7 | 100%
CALENDAR VIEW
Blender person-days | 87.5 |  | Yellow cells are inputs - change the team size and the weeks recalculate.
Blender artists assumed | 3
Blender calendar weeks (5-day week) | 5.8333
Infographic person-days | 21
Designers assumed | 1
Infographic calendar weeks | 4.2
Runtime/code person-days | 13.5
Total person-days (all routes) | 122.7
Total distinct assets | 107
Total animation clips | 48

## Risks & Decisions
Open decisions and schedule risks
Settle the top four before anyone opens Blender.
# | Decision / risk | Where it bites | Options | Recommendation | Cost of getting it wrong | Owner | Decide by
1 | Molten solder: real sim or baked? | B45; every fix in BC.3 | (a) Blender fluid sim, pre-rendered to video for that beat (b) baked vertex animation + animated emissive shader, stays interactive (c) skip the melt, cut straight to 'joint done' | (b) for the fixes, (a) only for the one hero close-up in Fix 2. Never (c) - 'lift only once it liquifies' is the skill. | Rework of 5 animation clips. ~8 days lost if discovered late. | 3D lead | Before Wave 4
2 | Hands on screen, or tools only? | Every BC.3 scene; storyboard says 'technician using...' | (a) model + rig hands (b) tool-only convention, instrument moves with no hands (c) real video inserts for the hand-skill beats | (b). Reads better at macro scale, it is what teardown videos do, and it saves 15-20 days plus constant clipping fixes. | 15-20 days and a permanent clipping problem across every fix. | Producer | Before Wave 1
3 | FPC ribbon deformation method | B10, A09 - the peel-off in Fix 3 | (a) Blender cloth sim (b) bone chain (c) shape keys (d) pre-rendered video | (b) bone chain, baked to glTF. Cloth sim does not survive export. A09 cannot start until this rig signs off. | A09 blocked. Fix 3 is the most misdiagnosed fault in the course - cannot ship it weak. | 3D lead | Before Wave 1
4 | Runtime: extend the existing three.js stack, or Unity WebGL? | Whole build | (a) React + three.js, same as the welding sim (b) Unity WebGL (c) pre-rendered video + 2D interaction only | (a) if the welding sim's runtime is reusable - you already have the shell, the language switcher and the step gating. | A second engine means a second asset pipeline and no shared components. | Eng lead | Before Wave 1
5 | Do the Charger IC internal stages get modelled? | I09; BC.1-S4 | (a) 2D block diagram (b) stylised 3D 'inside the chip' scene | (a). OVP, buck converter and current sense are functional blocks in silicon with no visible geometry. The supplied reference already shows the right treatment. | A week or more spent modelling something invented, that teaches less than the diagram. | Instructional lead | Before I09 starts
6 | YouTube links: embed, license, or reshoot? | V01-V04 | (a) link out (b) license (c) reshoot on your own bench | (c) for anything that ends up inside the assessed flow; (a) is fine for optional 'watch more'. | Rights exposure on a government-facing TVET product. | Content lead | Before BC.3 review
7 | Which handset does the 3D match? | B01, B02 - and therefore everything | (a) generic mid-range Android (b) match the realme unit in the supplied photos (c) several models | (a) generic, but photographed alongside the real realme shots (P02) so learners can bridge. (c) triples the asset count. | Learners trained on a board layout they never meet. Or 3x the modelling budget. | Instructional lead | Before Wave 1
8 | Asset weight on low-end Android | All Blender assets | (a) budget from day one: Draco + KTX2, 8MB per scene ceiling (b) optimise at the end | (a). Retrofitting compression across 51 assets is far more expensive than building to budget. | A course that will not load on the devices it was built for. | 3D lead | Before Wave 1
9 | Solder joint state set - in or out of scope? | B40 | (a) build all 5 states (b) good/bad only (c) skip | (a). 1.5 days for the highest teaching value per day on the whole list - it is what makes the diagnosis assessable. | No way to assess joint quality, which is most of the curriculum. | Instructional lead | Before Wave 4
10 | Two missing graphics (I24 fault tree, I28 fix ladder) | BC.3 as a whole | (a) add both (b) leave the storyboard as written | (a). 1.25 days combined. 'Start with the easiest thing first' is stated in the VO and never drawn. | Learners memorise six fixes without a map for choosing between them. | Instructional lead | Before BC.3 design
Amber rows are the four that block the start of modelling.